## Sheet1
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
Chronic Medical Issues | Chronic medical issues mean I may miss vital parts of sessions and generally have less time to complete the project. | Ensure that any medical procedures are kept out of working hours and have measures ready to ameliorate any crises that may arises. | Diminish deleterious effects of health issues on project completion. | Very Likely | Major
Acute Medical Issues/Force Majeur | An acute medical or other serious issue could mean significant damage to my ability to complete my project is at all. | Make back-up plans such as attempting to complete all issues to an MVP standard with debugging and enahncements coming later. | Diminish effect a serious unexpected event could have on achieving an MVP. | Very Unlikely | Catastrophic
Internent/Service Outage | Internet or other service outage close to the time of submission may mean that the project is not submitted on time. | Always update project on a submitted GitHub repo to ensure that minimal work is lost in the event that an outage occurs. | Lessen chance of missing a deadline or submitting incomplete work. | Unlikely | Negligible
PC Faliure | Any part of my PC may fail (e.g., hard drives, motherboard and so on). This could have disastrous consdequences if projects aren't backed up. | Frequently update GitHub and save copies of the project to my backup machine. | Mitigate any loss of progress due to a single point failure. | Moderate | Minor
Burnout | Working without breaks and adequate sleep may lead to burnout, which will vastly reduce my quality of work and increase the time needed to complete it. | Schedule project to allow for adequate sleep and a healthy distribution of workload over the allocated time. | Ensure that work remains stable throughout course of project and internal deadlines are met on time. | Moderate | Major